## Gantt Chart
Bangkit Capstone Project Schedule
PROJECT TITLE |  | Smart Waste Management System with Solar Cell-based IoT (Internet of Things) Concept to Support ESG Programs |  |  |  |  | Group ID | [6 empty] | C241-PS140
PROJECT TRACK |  | Product Track |  |  |  |  | DATE | [6 empty] | 2018-04-13
SELECTED THEME |  | Sustainable Futures: Nurturing harmony between humanity and the environment
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE (Month/Day/Year) | DUE DATE (Month/Day/Year) | DURATION |  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | Status | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Finishing Project Plan
1.1 | Excecutive Summary/Abstract | Rangga | 2024-04-24 | 2024-05-02 | 8 | On Track
1.2 | How did your team come up with this project? | Putri | 2024-04-24 | 2024-05-02 | 8 | On Track
1.3 | Project Scope & Deliverables | Mixed member | 2024-04-24 | 2024-05-02 | 8 | On Track
1.4 | Project Schedule | Mirza | 2024-04-24 | 2024-05-02 | 8 | On Track
1.5 | Based on your team’s knowledge, what tools/IDE/Library and resources that your team will use to solve the problem | Dylan | 2024-04-24 | 2024-05-02 | 8 | Completed
1.6 | Based on your knowledge and explorations, what will your team need support for? | Rosalia | 2024-04-24 | 2024-05-02 | 8 | On Track
1.7 | Based on your team’s planning, is there any identifiable potential Risk or Issue related to your project? | Mixed member | 2024-04-24 | 2024-05-02 | 8 | On Track
1.8 | Finishing and Polishing Project Plan Content | All member team | 2024-04-24 | 2024-05-13 | 19 | On Track
1.9 | Deadline Project Plan Submission | All member team | 2024-04-24 | 2024-05-13 | 19 | On Track
2 | Project Capstone Definition and Planning
2.1 | Scope and Goal Setting | All member team | 2018-03-24 | 2018-03-28 | 4
2.2 | Budget | All member team | 2018-03-29 | 2018-04-02 | 3
2.3 | Communication Plan | All member team |  |  | 0
2.4 | Risk Management | All member team |  |  | 0
3 | Project Conception and Initiation
3.1 | Status and Tracking | All member team |  |  | 0
3.2 | KPIs | All member team |  |  | 0
3.2.1 | Monitoring | All member team |  |  | 0
3.2.2 | Forecasts | All member team |  |  | 0
3.3 | Project Updates | All member team |  |  | 0
3.3.1 | Chart Updates | All member team |  |  | 0
4 | Project Performance / Monitoring
4.1 | Project Objectives | All member team |  |  | 0
4.2 | Quality Deliverables | All member team |  |  | 0
4.3 | Effort and Cost Tracking | All member team |  |  | 0
4.4 | Project Performance | All member team |  |  | 0